## Sheet1
Oasis Pain Clinic EHR Implementation
Tasks | Duration (Days) | Start Date | End Date | Responsibility
Installation
Vendor Visit | 3 | 2016-04-29 | 2016-05-02 | Project Manager
Hardware & Aplications | 2 | 2016-05-02 | 2016-05-04 | IT
Physician feedback | 2 | 2016-05-10 | 2016-05-12 | Project Manager, Practice Partners
Patient Information Management
Development Environment | 5 | 2016-05-15 | 2016-05-20 | IT
MPI | 10 | 2016-05-20 | 2016-05-30 | Head nurse, IT
Scheduling | 14 | 2016-06-05 | 2016-06-19 | Head nurse, IT
Lab | 14 | 2016-06-10 | 2016-06-24 | Head nurse, IT
Parmacy | 14 | 2016-06-20 | 2016-07-04 | Head nurse, IT
Testing
Unit and function testing | 21 | 2016-07-05 | 2016-07-26 | Project Manager, Vendor, IT
System test | 30 | 2016-07-10 | 2016-08-09 | Project Manager, Physician, Nurse
Interface testing(iPads) | 7 | 2016-07-20 | 2016-07-27 | Phycisians, IT
Performance and stress testing | 14 | 2016-07-29 | 2016-08-12 | IT
Training
Front office staff | 30 | 2016-08-01 | 2016-08-31 | Front Office Manager, IT
Back office/Billing | 30 | 2016-08-08 | 2016-09-07 | Head nurse, IT
Nurses | 30 | 2016-08-15 | 2016-09-14 | Project Manager, Head Nurse
Pysicians | 30 | 2016-08-22 | 2016-09-21 | Project Manager, Practice Partners
Go Live
Aduditing | 7 | 2016-09-12 | 2016-09-19 | IT
User Satisfaction Survey | 14 | 2016-09-19 | 2016-10-03 | Project Manager, Head Nurse
Patient Satisfaction Survey | 14 | 2016-10-02 | 2016-10-16 | Front Office Manager
Formulas:
End Date = [Start Date]+[Duration (Days)]